## Summary Report
Test Summary Report
Test Report |  | System Test
EXECUTED | PASSED |  |  |  | 144 |  |  | PASSED | 144
| FAILD |  |  |  | 15 |  |  | FAILED | 15
| TOTAL TEST EXECUTED (PASSED + FAILD) |  |  |  | 159
PINNDING |  |  |  |  | 0
IN PROGRESS |  |  |  |  | 0
BLOCKED |  |  |  |  | 0
SUBTOTAL TEST PLANNED (PENNDING + IN PROGRESS + BLOCKED + TEST EXECUTED) |  |  |  |  | 159
Function | Description | % TC Executed | % TC Passed | % TC Pending | No. TC Executed | No. TC Passes | Priority
Add Contact | Create a new contact by sending contact details in the request body and requires authentication. | 100% | 85% | 0% | 20 | 17 | High
Get Contact List | Recive all contacts and requires authentication. | 100% | 100% | 0% | 9 | 9 | High
Get Contact | Recive a specific contact by ID from the contact list and requires authentication. | 100% | 100% | 0% | 12 | 12 | High
Update Contact (PUT) | Update a contact by sending all contact details in the request body and Requires authentication. | 100% | 84% | 0% | 13 | 13 | High
Update Contact (PATCH) | Partially update a contact by sending the fields to update in the request body andRequires authentication. | 100% | 100% | 0% | 44 | 36 | High
Delete Contact | Delete a specific contact by ID and Requires authentication. | 100% | 100% | 0% | 4 | 4 | High
Add User | Create a new user by sending user details (first name, last name, email, password) in the request body. | 100% | 100% | 0% | 8 | 8 | High
Get User Profile | Retrieve the authenticated user's profile details. This operation requires authentication using a Bearer token. | 100% | 100% | 0% | 8 | 8 | High
Update User | Update the authenticated user's profile (first name, last name, email, password) using data sent in the request body. Requires authentication using a Bearer token. | 100% | 77% | 0% | 13 | 10 | High
Log Out User | Let users to log out using a valid token. After logout, the token must be cancelled and any additional use of the same token must be rejected | 100% | 100% | 0% | 8 | 8 | High
Log In User | Let users to log in with valid IDs and get an authentication token, Reject incorrect, missing, or invalid inputs, Token must be saved securely and used for authorized requests | 100% | 90% | 0% | 10 | 9 | High
Delete User | Let a logged-in user to delete their own account using a valid token. The deleted user's data must be removed, and the token should become invalid. Future login or requests with the same credentials must fail | 100% | 100% | 0% | 10 | 10 | High